## Product Backlog
ID | Title | Type | Priority | MoSCoW | Source | Effort Estimate | RICE Score | User Story | Description | Acceptance Criteria
BL-001 | Rich Session Dashboard | Feature | High | Should Have | PRD Deferred | Medium (3-5 days) | 126 | As a user, I want a detailed session dashboard with quiz attempt counts, last activity date, and completion status so that I can better track my progress within each session. | Enhance the basic session view with richer metadata: quiz attempt count per session, last activity timestamp, visual completion indicators, and summary statistics per session. | Session dashboard shows: number of quiz attempts, last activity date, score distribution across attempts, difficulty levels attempted. Visual indicators for session activity level.
BL-002 | Progressive Difficulty Prompts | Feature | High | Should Have | PRD Deferred | Small (1-2 days) | 108 | As a user, I want the system to suggest trying harder difficulty levels when I perform well so that I naturally progress in my skills. | After completing a quiz with a high score (e.g., >80%), prompt the user to try the same topic at a harder difficulty. Provide a one-click option to generate a new quiz at the next difficulty level. | If score >80%, show suggestion to try next difficulty. One-click generation at higher difficulty. Suggestion is dismissible. Does not appear if already at Hard.
BL-003 | Interview Simulation Session | Feature | High | Should Have | PRD Deferred | Very Large (weeks+) | 72 | As a user, I want to start an interview prep session based on current real-world interview questions and trends for my target role, so that I can practice with questions similar to what companies are actually asking. | New session type that generates exercises based on researched real-world interview questions rather than uploaded materials. Requires web research pipeline, interview question curation, company/role-specific targeting. | User can create an 'Interview Simulation' session by specifying target role and companies. System generates questions based on current interview trends. Questions reflect AI-era interview formats. Source attribution for question inspiration.
BL-004 | Google Login / OAuth | Feature | Medium | Should Have | PRD Deferred | Medium (3-5 days) | 90 | As a user, I want to sign up and log in with my Google account so that I can access the product without creating a separate account. | Implement Google OAuth 2.0 for signup and login. Link Google accounts to existing email accounts if the email matches. Maintain email/password as an alternative. | Google sign-in button on login/signup page. New users auto-create account from Google profile. Existing users with matching email can link accounts. Email verification bypassed for Google-verified emails.
BL-005 | Analytics & Weak Area Detection | Feature | Medium | Could Have | PRD Deferred | Large (1-2 weeks) | 48 | As a user, I want to see my performance trends and which areas I'm weakest in so that I can focus my study time effectively. | Track performance across quizzes by topic/skill area. Categorize questions by skill (e.g., time complexity, system design, bug finding). Visualize trends over time. Identify weakest areas and recommend focus topics. | Dashboard shows: performance over time (chart), breakdown by skill category, weakest 3 areas highlighted, recommended next actions. Data based on all quiz attempts across all sessions.
BL-006 | Quiz Sharing / Export | Feature | Low | Could Have | Business Strategy | Small (1-2 days) | 30 | As a user, I want to share my quiz results with peers or export them as a PDF so that I can discuss my progress or use them for study groups. | Allow users to generate a shareable link for quiz results (read-only view) or export results as a PDF document. | Share button on quiz results page. Generates public read-only link. PDF export includes questions, user answers, correct answers, and feedback. Shared links do not require login to view.
BL-007 | Bookmark / Flag Questions | Feature | Low | Could Have | Business Strategy | Small (1-2 days) | 36 | As a user, I want to bookmark or flag questions I found difficult so that I can review them later and focus on my weak points. | Add a flag/bookmark toggle on each question during quiz-taking and on the results page. Create a 'Flagged Questions' view accessible from the session dashboard. | Flag icon on each question (during quiz and on results). Flagged questions viewable from session dashboard. User can unflag questions. Flagged questions list shows question, correct answer, and feedback.
BL-008 | Custom LLM Prompt Spec Editor | Feature | Low | Could Have | Business Strategy | Medium (3-5 days) | 20 | As an advanced user, I want to customize the types of questions generated (e.g., more system design, fewer bug-finding) so that I can focus my practice on specific skill areas. | Allow users to adjust the question type distribution within a session. For example, slider controls for: % bug finding, % code evaluation, % system design, % algorithm selection. | Configuration panel accessible before quiz generation. Sliders or checkboxes for question type distribution. Percentages must sum to 100%. Saved as session-level preference.
BL-009 | Video Explanation Generation | Feature | Nice to have | Won't Have Yet | PRD Deferred | Very Large (weeks+) | 8 | As a user, I want to generate a short explanatory video summarizing my uploaded material so that I can understand the content visually before practicing. | Generate short (2-5 min) explainer videos from uploaded text content using AI video generation. Videos include visuals, simplified explanations, and examples. Requires video generation pipeline, significant infrastructure. | User can request video from uploaded materials. Video generated within 5 minutes. Video includes visual aids and simplified explanations. Video playable in-app. Deferred until user research validates demand.
BL-010 | B2B API & Bootcamp Integration | Feature | Nice to have | Won't Have Yet | PRD Deferred | Very Large (weeks+) | 10 | As a bootcamp program director, I want to integrate the skills trainer into our curriculum so that students get structured AI-era interview preparation as part of their program. | API layer allowing bootcamps to integrate quiz generation and results into their LMS. Admin dashboard for instructors. Cohort management. Bulk user provisioning. Usage analytics per cohort. | REST API for quiz generation and results retrieval. Admin dashboard with cohort overview. Instructor can assign sessions to students. Bulk invite via email. API documentation provided.
BL-011 | Mobile Native App | Feature | Nice to have | Won't Have Yet | Business Strategy | Very Large (weeks+) | 12 | As a user, I want to practice on my phone so that I can study during commutes or downtime. | Native iOS and Android application with full feature parity to the web app. Push notifications for study reminders. Offline mode for reviewing past results. | Available on iOS and Android. Feature parity with web app. Push notifications for study reminders. Offline access to past quiz results. Responsive and performant on mobile devices.
BL-012 | Payment & Subscription System | Feature | Nice to have | Won't Have Yet | Business Strategy | Large (1-2 weeks) | 15 | As a product owner, I want to implement a freemium model with subscription tiers so that the product can generate revenue. | Implement Stripe or similar payment processing. Define free tier limits (e.g., 3 sessions, 5 quizzes/month) and paid tier features. Subscription management, billing, and invoicing. | Free tier with defined limits. Paid tier with expanded access. Stripe integration for payment. Subscription management page. Upgrade/downgrade flow. Invoice generation.
BL-013 | LLM Prompt Spec Optimization | Improvement | Critical | Should Have | Risk Mitigation | Large (1-2 weeks) | 200 | N/A - Technical task | Iteratively refine the LLM prompt specification for question generation and free-text grading. Test across 50+ questions at each difficulty level. Validate question quality and grading accuracy with 3-5 real users. Document the final spec. | 50+ test questions generated at each difficulty level reviewed for quality. Grading tested with 10+ sample free-text answers at varying quality. Question quality rated 4+/5 by test users. Grading accuracy validated as fair by test users. Final prompt spec documented.
BL-014 | User Research - Post-Launch Validation | Improvement | Critical | Should Have | Risk Mitigation | Medium (3-5 days) | 180 | N/A - Research task | Conduct structured interviews with 10-15 bootcamp graduates using the interview guide from the PRD. Validate core assumptions: (1) interview failure tied to evaluation/architecture skills, (2) users engage repeatedly, (3) willingness to pay. | 10-15 interviews completed. Findings documented. Problem hypothesis confirmed or revised. Product adjustments identified if needed.
BL-015 | Collaborative Study Sessions | Feature | Nice to have | Won't Have Yet | Business Strategy | Very Large (weeks+) | 6 | As a user, I want to create study sessions with friends so that we can practice together and discuss our approaches. | Shared sessions where multiple users can take the same quiz and compare results. Discussion threads per question. Leaderboard within the group. | Invite peers to a session via email or link. All members take the same generated quiz. Comparative results view. Per-question discussion thread. Group leaderboard.

## RICE Scoring
ID | Title | Reach (users/month) | Impact (0.25-3) | Confidence (%) | Effort (person-weeks) | RICE Score
BL-013 | LLM Prompt Spec Optimization | 30 | 3 | 100 | 2 | 45
BL-014 | User Research - Post-Launch Validation | 30 | 3 | 100 | 1 | 90
BL-001 | Rich Session Dashboard | 25 | 2 | 80 | 0.5 | 80
BL-002 | Progressive Difficulty Prompts | 25 | 2 | 80 | 0.37 | 108
BL-004 | Google Login / OAuth | 30 | 1.5 | 80 | 0.6 | 60
BL-003 | Interview Simulation Session | 20 | 3 | 50 | 4 | 8
BL-005 | Analytics & Weak Area Detection | 20 | 2 | 50 | 2 | 10
BL-007 | Bookmark / Flag Questions | 20 | 1 | 80 | 0.37 | 43
BL-006 | Quiz Sharing / Export | 15 | 1 | 80 | 0.37 | 32
BL-008 | Custom LLM Prompt Spec Editor | 15 | 1 | 50 | 0.6 | 13
BL-012 | Payment & Subscription System | 10 | 1.5 | 50 | 2 | 4
BL-011 | Mobile Native App | 15 | 1 | 50 | 6 | 1
BL-010 | B2B API & Bootcamp Integration | 5 | 2 | 50 | 6 | 1
BL-009 | Video Explanation Generation | 10 | 1 | 30 | 8 | 0
BL-015 | Collaborative Study Sessions | 10 | 1 | 30 | 6 | 1

## MVP Stories (Reference)
Story # | Title | Status | Priority
1 | Account Creation (email/password, verification) | MVP | Must Have
2 | Create Learning Session (with Home Dashboard & session list) | MVP | Must Have
3 | Upload Study Materials (optional, PDF/DOCX/TXT/URL) | MVP | Must Have
4 | Configure Quiz Preferences (format, difficulty, count) | MVP | Must Have
5 | Generate Critical Evaluation Exercises | MVP | Must Have
6 | Take Exercises (scrollable list with navigation panel) | MVP | Must Have
7 | Submit and Review Results with Explanations | MVP | Must Have